## S_013122
Task | Category | Name | Date | start | end
1.1 | Research and Data Collection | Determine current water supply and demands | January 18, 2022 → January 24, 2022 | 2022-01-18 | 2022-01-24
1.2 | Research and Data Collection | Determine increased demands | January 25, 2022 → January 31, 2022 | 2022-01-25 | 2022-01-31
1.3 | Research and Data Collection | Determine if current supply will meet increased demands | January 29, 2022 → February 2, 2022 | 2022-01-29 | 2022-02-02
2.1 | Design and Analysis | Peak demand | February 2, 2022 → February 8, 2022 | 2022-02-02 | 2022-02-08
2.2 | Design and Analysis | Fire flow | February 7, 2022 → February 12, 2022 | 2022-02-07 | 2022-02-12
2.3 | Design and Analysis | Check if additional pumps and tanks are needed | February 13, 2022 → February 20, 2022 | 2022-02-13 | 2022-02-20
2.4 | Design and Analysis | Pipe sizing | February 19, 2022 → February 24, 2022 | 2022-02-19 | 2022-02-24
2.5 | Design and Analysis | System curve development, NPSH calculations for pump selection | February 20, 2022 → February 25, 2022 | 2022-02-20 | 2022-02-25
2.6 | Design and Analysis | Tank sizing to meet fire and daily demands | February 21, 2022 → February 26, 2022 | 2022-02-21 | 2022-02-26
3.1 | Plans and Profiles | Create graphic of proposed improvements | February 22, 2022 → February 27, 2022 | 2022-02-22 | 2022-02-27
3.2 | Plans and Profiles | Create a schedule of improvements | February 26, 2022 → March 5, 2022 | 2022-02-26 | 2022-03-05
3.3 | Plans and Profiles | EGL and HGL calculations and drawings | February 28, 2022 → March 5, 2022 | 2022-02-28 | 2022-03-05
4.1 | Cost Estimation | Materials | March 4, 2022 → March 11, 2022 | 2022-03-04 | 2022-03-11
4.2 | Cost Estimation | Construction | March 11, 2022 → March 19, 2022 | 2022-03-11 | 2022-03-19
5.1 | Documentation | Engineers Report | March 21, 2022 → April 16, 2022 | 2022-03-21 | 2022-04-16