## SSF_1
Name | Number | Title | Tags | Type | S_M | S_Q | E_M | E_Q | start | end | Priority | Completion | Month | Quarter | Starts | Ends
Task 1 | 1 | V&A - Finalize Basin R-Values | Sewer System Master Plan | Deliverable | 1 | 3 | 1 | 4 | 1/17/2022 | 2/1/2022 | 1 | 43 | Jan | 1 | 1 | 9
Task 2 | 2 | Update Condition Assessment and CIP | Sewer System Master Plan | Deliverable | 1 | 4 | 2 | 3 | 1/24/2022 | 2/24/2022 | 2 | 13 | Jan | 2 | 9 | 17
Task 3 | 3 | Update Draft SSMP Report | Sewer System Master Plan | Deliverable | 2 | 2 | 2 | 4 | 2/9/2022 | 3/1/2022 | 3 | 56 | Feb | 3 | 17 | 24
Task 4 | 4 | Prepare Final SSMP Report | Sewer System Master Plan | Deliverable | 3 | 3 | 3 | 3 | 3/17/2022 | 3/24/2022 | 2 | 90 | Mar | 4 | 24 | 1
Task 4 | 4 | Prepare Final SSMP Report | Sewer System Master Plan | City Review | 3 | 1 | 3 | 2 | 3/1/2022 | 3/17/2022 | 2 | 90 | Mar
Task BW1 | 5 | BWA Draft to AEG | Capacity Fee Study (Bartle Wells) | Deliverable | 1 | 3 | 1 | 3 | 1/17/2022 | 1/24/2022 | 4 | 100 | Jan
Task BW2 | 6 | AEG & BWA Web conference | Capacity Fee Study (Bartle Wells) | Deliverable | 1 | 4 | 1 | 4 | 1/24/2022 | 2/1/2022 | 5 | 23 | Jan
Task BW3 | 7 | AEG, BWA, & SSF Web conference | Capacity Fee Study (Bartle Wells) | Deliverable | 2 | 1 | 2 | 1 | 2/1/2022 | 2/9/2022 | 1 | 56 | Feb
Task BW4 | 8 | Complete Analysis and Report | Capacity Fee Study (Bartle Wells) | Deliverable | 2 | 1 | 2 | 3 | 2/1/2022 | 2/24/2022 | 1 | 88 | Feb
Task BW5 | 9 | City Council Presentation | Capacity Fee Study (Bartle Wells) | Deliverable | 2 | 4 | 2 | 4 | 2/24/2022 | 3/1/2022 | 2 | 33 | Feb
Task BW6 | 10 | Public Hearing to Adopt Fees | Capacity Fee Study (Bartle Wells) | Deliverable | 3 | 4 | 3 | 4 | 3/24/2022 | 4/1/2022 | 3 | 66 | Mar
Task BW6 | 10 | Public Hearing to Adopt Fees | Capacity Fee Study (Bartle Wells) | Notification Period | 3 | 1 | 3 | 3 | 3/1/2022 | 3/24/2022 | 3 | 66 | Mar
Task BW7 | 11 | New Fee Effective Date | Capacity Fee Study (Bartle Wells) | Deliverable | 6 | 1 | 6 | 1 | 6/1/2022 | 6/9/2022 | 2 | 22 | Jun
Task BW7 | 11 | New Fee Effective Date | Capacity Fee Study (Bartle Wells) | Notification Period | 4 | 1 | 5 | 4 | 4/1/2022 | 6/1/2022 | 2 | 22 | Apr